SPRINT DEVELOPMENT PLAN Batch ETL Pipeline — Market Analysis System (E-Commerce)

# PROJECT OVERVIEW

| Sprint | Focus | Key Deliverable | Timeline | Status |
| --- | --- | --- | --- | --- |
| Sprint 1 | Foundation + Extraction | Docker + running extractor | Day 1–10 | In process |
| Sprint 2 | Transform + Load | Clean data in PostgreSQL | Day 8–18 | Not started |
| Sprint 3 | Airflow Orchestration | Scheduled, resilient DAG | Day 16–24 | Not started |
| Sprint 4 | Dashboard + Hardening | Live dashboard + tested code | Day 23–30 | Not started |

| 30 Days Total Duration | 4 Sprints Development Cycles | 7 Phases From SRS Document | 30+ Tasks Detailed Work Items |
| --- | --- | --- | --- |

GANTT CHART — 30-DAY TIMELINE

| Task / Sprint | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1: Foundation + Extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 2: Transform + Load |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 3: Orchestration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sprint 4: Visualization + Hardening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Buffer / Integration Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Week → | Week 1 |  |  |  |  |  |  | Week 2 |  |  |  |  |  |  | Week 3 |  |  |  |  |  |  | Week 4 |  |  |  |  |  |  |  |  |

Legend: ■ Sprint 1  ■ Sprint 2  ■ Sprint 3  ■ Sprint 4  ■ Buffer

| # SPRINT 1 — FOUNDATION & DATA EXTRACTION Phase 1 + Phase 2 ¦ Timeline: Day 1–10 | Week 1–2 |
| --- | --- |

SPRINT GOAL

By end of Sprint 1, the developer can: - Run the full Docker Compose stack (Airflow + PostgreSQL + Metabase) locally - Execute a Python script that fetches real product data from the chosen source - Verify that raw data is saved to a staging file (JSON/CSV) - Confirm PostgreSQL tables are created with correct schema

PHASE 1 — Infrastructure & Environment Setup (Day 1–4)

| Day 1 Mon | Tasks & Deliverables |
| --- | --- |
| SETUP | Project Repository & Environment Bootstrap - Create Git repository: ecommerce-etl with main + develop branches - Initialise Python virtual environment (Python 3.11+) and requirements.txt - Create .env.example and .gitignore (exclude .env, staging/, __pycache__) - Set up project folder structure from SRS Section 6 exactly - Commit initial scaffold with README.md stub |

| Day 2 Tue | Tasks & Deliverables |
| --- | --- |
| CONFIG | Docker Compose Stack Setup - Write docker-compose.yml with services: postgres, airflow-webserver, airflow-scheduler, airflow-init, metabase - Use apache/airflow:2.7.3-python3.11 as base image - Configure Airflow with LocalExecutor + PostgreSQL as metadata DB - Set environment variables: AIRFLOW_UID, POSTGRES_USER, POSTGRES_PASSWORD, POSTGRES_DB - Run: docker compose up airflow-init && docker compose up -d — verify Airflow UI at localhost:8080 |

| Day 3 Wed | Tasks & Deliverables |
| --- | --- |
| DB | PostgreSQL Schema Initialisation - Write sql/create_tables.sql with all 3 tables: products_market, pipeline_runs, rejected_records - Add UNIQUE constraint on products_market(product_id, source, extraction_date) for UPSERT dedup - Create indexes: idx_products_category, idx_products_extraction_date, idx_pipeline_runs_date - Write a Python script scripts/init_db.py that connects via SQLAlchemy and executes create_tables.sql - Run init_db.py inside container and verify tables exist with \dt in psql |

Notes: 2 options for DB

- Option A: psql inside the container (docker): optimized for current stage   recommended

- simpler

  - no extra service to configure

  - no extra ports, credentials, or browser login

- more reliable

  - if Postgres is running, psql will work

  - avoids pgAdmin connection/password confusion

- closer to real ETL workflow

  - you will often run init scripts, checks, and debugging from terminal anyway

- faster for Day 3

  - your task is to create schema and verify tables, not do visual admin work

- lighter

  - pgAdmin adds another container and uses more memory

- Option B: Add pgAdmin to Docker Compose (GUI, good for visualising tables)

  browsing tables visually

  manually editing rows

  inspecting constraints/indexes with clicks

  showing screenshots in demos

| Day 4 Thu | Tasks & Deliverables |
| --- | --- |
| CONFIG | Airflow Connections & Variables Setup - Create Airflow Connection: postgres_ecommerce pointing to PostgreSQL container - Create Airflow Variables: DATA_SOURCE_URL, STAGING_DIR, SLACK_WEBHOOK_URL (stub), MAX_RETRIES - Create Airflow Variable: PIPELINE_ENV (dev / prod) - Write etl/config.py that reads all config from Airflow Variables and os.environ - Test: write a minimal test DAG hello_world_dag.py — confirm it runs green in Airflow UI |

PHASE 2 — Data Extraction Module (Day 5–10)

| Day 5 Fri | Tasks & Deliverables |
| --- | --- |
| CODE | Data Source Research & Connector Design - Finalize data source choice (recommended: FakeStoreAPI for dev + Tiki for demo) - Manually inspect API response: document all fields returned, their types, and pagination pattern - Design BaseExtractor abstract class in etl/extractor.py with extract(), validate_response(), save_raw() methods - Write config/schema_spec.yaml listing expected columns and types - Document data source in README under 'Data Sources' section |

| Day 6–7 Sat–Sun | Tasks & Deliverables |
| --- | --- |
| CODE | FakeStoreAPI Extractor Implementation - Implement FakeStoreExtractor(BaseExtractor) in etl/extractor.py - Implement pagination loop: fetch all pages until empty response or page limit reached - Add requests.Session() with timeout=30, headers={'User-Agent': '...'} - Add extraction_timestamp and source fields to every row during extraction - Save raw data to staging/{execution_date}/raw_products.json atomically (write to .tmp then rename) - Log: rows fetched per page, total rows, request duration |
| CODE | Rate Limiting & Retry Decorator - Write utils/retry.py with @retry_with_backoff(max_retries=3, base_delay=30) decorator - Implement exponential backoff: delay = base_delay * (2 ** attempt) with jitter (random 0–5s) - Handle: requests.Timeout, requests.ConnectionError, HTTP 429, HTTP 5xx separately - Write unit test: mock requests to raise Timeout on first 2 calls, succeed on 3rd — assert success |

| Day 8–9 Mon–Tue | Tasks & Deliverables |
| --- | --- |
| CODE | (Optional Bonus) Web Scraping Extractor — Shopee/Tiki - If choosing scraping: implement TikiScraper using requests + BeautifulSoup - Add 1.5s sleep between page requests to avoid rate limiting - Rotate User-Agent from a list of 5 real browser UA strings - Extract: product_id from URL, name, price, rating, review_count, category from HTML - Gracefully skip products with missing required fields (log warning, do NOT raise) - Save to staging/{date}/raw_tiki_products.json alongside API data |

| Day 10 Wed | Tasks & Deliverables |
| --- | --- |
| TEST | Extraction Module Testing & Sprint 1 Review - Write tests/test_extractor.py: mock HTTP responses with responses library or unittest.mock - Test cases: normal success, timeout retry, 429 backoff, empty response, malformed JSON - Run pytest tests/test_extractor.py -v — ensure 0 failures - Manual integration test: run extractor against live API, verify staging file is created - Sprint 1 review: check all DoD items below, commit and push all work |

SPRINT 1 — DEFINITION OF DONE

| # | Definition of Done — Acceptance Criterion | Status |
| --- | --- | --- |
| 1 | docker compose up brings Airflow UI, PostgreSQL, and Metabase online without errors | Finished |
| 2 | All 3 PostgreSQL tables created with correct schema and constraints (verified with \dt + \d table_name) | Not started |
| 3 | Airflow Connection postgres_ecommerce and all Variables are configured | Not started |
| 4 | extractor.py fetches real data and saves raw JSON to staging/ directory | Not started |
| 5 | Retry decorator correctly retries on timeout/5xx with exponential backoff (unit test passes) | Not started |
| 6 | tests/test_extractor.py: all tests pass with 0 failures | Not started |
| 7 | No credentials or secrets committed to Git (grep check passes) | Not started |
| 8 | README updated with 'Getting Started' section covering Docker Compose setup | Not started |

| # SPRINT 2 — TRANSFORMATION & LOADING Phase 3 + Phase 4 ¦ Timeline: Day 8–16 | Week 2–3 of 4 sprints |
| --- | --- |

SPRINT GOAL

By end of Sprint 2, the developer can: - Take raw JSON from staging and produce a clean, validated Pandas DataFrame - Load clean data into PostgreSQL with UPSERT (no duplicates on re-run) - Every rejected row is recorded in rejected_records with a reason - Every pipeline run is logged in pipeline_runs with row counts and status

PHASE 3 — Data Transformation Module (Day 8–13)

| Day 8–9 Mon–Tue | Tasks & Deliverables |
| --- | --- |
| CODE | Core Cleaning Pipeline — transformer.py - Create etl/transformer.py with class DataTransformer accepting raw DataFrame - Implement step 1: drop_invalid_rows() — remove rows where product_id or price is NULL/empty - Implement step 2: normalize_price() — cast to float, round 2dp, reject rows with price <= 0 - Implement step 3: normalize_category() — lowercase, replace spaces with _, strip special chars - Implement step 4: validate_rating() — clip to [0.0, 5.0], log rows that were clipped - Implement step 5: fill_defaults() — review_count=0, stock_status='unknown' for missing - Add pipeline_run_id UUID column to every row for full traceability |

| Day 10 Wed | Tasks & Deliverables |
| --- | --- |
| CODE | Schema Validation with Pandera - Install pandera: add to requirements.txt - Write config/schema_spec.py defining DataFrameSchema with expected column types and checks - Integrate schema validation into transformer.py: run after all cleaning steps - On schema error: log the schema diff (added/removed columns), raise SchemaError to halt pipeline - Write tests/test_transformer.py: test each cleaning step with crafted dirty DataFrames |
| CODE | Rejected Records Tracking - Create utils/rejection_logger.py with append_rejected(run_id, raw_row, reason) function - Capture rejected rows at each cleaning step before dropping them - Accumulate into a rejected_df and bulk-insert into rejected_records table at end of transform - Log summary: 'Rejected N rows: {reason: count} breakdown' |

| Day 11 Thu | Tasks & Deliverables |
| --- | --- |
| CODE | Data Quality Score Metric (Bonus) - After transformation, calculate data_quality_score = rows_loaded / rows_extracted * 100 - Store score in pipeline_runs.data_quality_score (add column to schema) - Add threshold check: if score < 70%, log WARNING and consider alerting stakeholders - Write unit test: verify score calculation for known input/output row counts |

PHASE 4 — Data Loading Module (Day 12–18)

| Day 12–13 Fri–Sat | Tasks & Deliverables |
| --- | --- |
| CODE | PostgreSQL Loader with UPSERT — loader.py - Create etl/loader.py with class DataLoader(engine: SQLAlchemy engine) - Implement load_products(df, run_id) using SQLAlchemy Core INSERT ... ON CONFLICT DO UPDATE - CONFLICT target: (product_id, source, extraction_date) — the UNIQUE constraint from Day 3 - UPDATE SET: price, rating, review_count, stock_status, updated_at = EXCLUDED.updated_at - Wrap entire load in a single transaction: rollback on any exception - Return count of rows actually inserted vs updated for pipeline_runs log |
| CODE | Pipeline Runs Logger - Implement log_run_start(run_id, dag_id, execution_date) → INSERT row into pipeline_runs - Implement log_run_end(run_id, status, counts_dict, error_msg=None) → UPDATE the row - Use status enum: 'SUCCESS', 'FAILED', 'PARTIAL' - Ensure log_run_end is always called even if load fails (use try/finally pattern) |

| Day 14–15 Sun–Mon | Tasks & Deliverables |
| --- | --- |
| TEST | End-to-End Integration Test (Extract → Transform → Load) - Write tests/test_integration.py spinning up a real test PostgreSQL via Docker or pytest fixtures - Test scenario 1 (Happy path): run E→T→L, verify row count in products_market matches input - Test scenario 2 (Idempotency): run same data twice, verify row count does NOT increase - Test scenario 3 (Partial failure): corrupt 20% of rows, verify clean rows loaded, corrupt rows in rejected_records - Test scenario 4 (DB disconnect): mock DB connection drop mid-load, verify rollback and no partial data - Run pytest tests/ -v --tb=short — 0 failures required before Sprint 2 closes |

| Day 16–18 Tue–Thu | Tasks & Deliverables |
| --- | --- |
| CODE | Staging Archive & Raw Data Preservation - After successful load, move raw JSON from staging/ to archive/{year}/{month}/{date}/ directory - Implement cleanup policy: delete archive files older than 90 days (configurable via Airflow Variable) - Add file integrity check: compute MD5 checksum of raw file before and after archiving - Log: 'Archived {filename} ({size}MB) to {path}' |
| REVIEW | Sprint 2 Code Review & Refactor - Run flake8 etl/ and fix all PEP8 warnings - Ensure every public function has a docstring - Review test coverage: run pytest --cov=etl tests/ — target >= 80% - Refactor any functions longer than 40 lines into smaller helpers - Update CHANGELOG.md and commit tagged release: v0.2.0-sprint2 |

SPRINT 2 — DEFINITION OF DONE

| # | Definition of Done — Acceptance Criterion | Status |
| --- | --- | --- |
| 1 | Running raw JSON through transformer.py produces a clean DataFrame with 0 invalid rows remaining | ☐ Pending |
| 2 | Re-running load_products() with identical data produces exactly 0 new rows (idempotency verified) | ☐ Pending |
| 3 | Rejected rows appear in rejected_records table with correct rejection_reason | ☐ Pending |
| 4 | Every pipeline run creates a row in pipeline_runs with accurate rows_extracted, loaded, rejected counts | ☐ Pending |
| 5 | DB connection failure triggers full rollback — no partial data in products_market | ☐ Pending |
| 6 | tests/test_transformer.py + tests/test_integration.py: all tests pass | ☐ Pending |
| 7 | pytest --cov=etl reports >= 80% coverage across etl/ modules | ☐ Pending |
| 8 | flake8 etl/ returns 0 warnings | ☐ Pending |

| # SPRINT 3 — ORCHESTRATION & ERROR HANDLING Phase 5 ¦ Timeline: Day 14–21 | Week 3 of 4 sprints |
| --- | --- |

SPRINT GOAL

By end of Sprint 3, the developer can: - Trigger the full ETL pipeline from Airflow UI with one click - The DAG runs automatically every day at 00:00 UTC without manual intervention - Any task failure triggers an alert (email or Slack message) - Simulate network failure → pipeline retries and recovers automatically - Backfill works: re-run DAG for a past date produces correct historical data

PHASE 5 — Apache Airflow Orchestration (Day 14–24)

| Day 16–17 Tue–Wed | Tasks & Deliverables |
| --- | --- |
| CODE | Main DAG Definition — ecommerce_market_etl - Create dags/ecommerce_market_dag.py - Configure DAG: schedule_interval='0 0 * * *', start_date, catchup=False (change to True for backfill demo), max_active_runs=1 - Define default_args: owner, retries=3, retry_delay=timedelta(minutes=5), retry_exponential_backoff=True - Create 5 tasks using PythonOperator: extract_data, validate_schema, transform_data, load_to_db, notify_status - Set task dependencies: extract >> validate >> transform >> load >> notify - Confirm DAG appears in Airflow UI with correct graph structure |

| Day 18 Thu | Tasks & Deliverables |
| --- | --- |
| CODE | Task Implementations — Airflow Operators - extract_data task: call FakeStoreExtractor.extract(ds=context['ds']), pass run_id via XCom - validate_schema task: load staging file, run pandera schema check — mark FAILED if schema drift - transform_data task: call DataTransformer.transform(), save clean parquet/CSV to staging - load_to_db task: call DataLoader.load_products(), log pipeline_runs row via XCom-passed run_id - notify_status task: always runs (trigger_rule=TriggerRule.ALL_DONE) — sends success or failure summary |
| CODE | XCom Data Passing Between Tasks - Push run_id UUID from extract_data task via ti.xcom_push(key='run_id', value=run_id) - Pull run_id in load_to_db and notify_status via ti.xcom_pull(task_ids='extract_data', key='run_id') - Push row counts dict from transform_data to notify_status for inclusion in alert message |

| Day 19–20 Fri–Sat | Tasks & Deliverables |
| --- | --- |
| CODE | Error Handling — All 8 Scenarios from SRS - Network timeout: requests timeout=30 + Airflow retry_delay with retry_exponential_backoff=True - HTTP 429: detect in extractor, raise RateLimitError, Airflow catches and retries after 60s - HTTP 5xx: log warning + send Slack alert + mark task FAILED after max retries - Duplicate on re-run: UPSERT logic already handles this — verify with a manual re-run test - NULL critical fields: rejection logger already handles this in transformer - DB disconnect mid-load: SQLAlchemy transaction rollback — verify pipeline_runs shows FAILED - Schema mismatch: pandera in validate_schema task catches this, halts pipeline before transform - Airflow worker timeout: set execution_timeout=timedelta(minutes=30) per task |

| Day 21 Sun | Tasks & Deliverables |
| --- | --- |
| CODE | Slack / Email Notifications - Create etl/notifier.py with send_slack_alert(webhook_url, message, status) function - On DAG SUCCESS: send green message with run_id, rows loaded, data quality score, duration - On DAG FAILURE: send red message with failing task name, error summary, Airflow log URL - Set on_failure_callback=notify_failure on default_args for automatic failure alerts - Test: manually mark a task as FAILED in Airflow UI — verify Slack message is received |

| Day 22–23 Mon–Tue | Tasks & Deliverables |
| --- | --- |
| TEST | Backfill Testing & Full Pipeline End-to-End - Enable catchup=True temporarily, set start_date 7 days ago — trigger backfill via Airflow CLI - Verify 7 separate pipeline_runs rows created with correct execution_date per day - Verify products_market has data for each of the 7 backfilled dates - Disable catchup=True after backfill demo — restore to False for production - Run full E2E test: unplugging Docker network mid-extract → verify retry → verify recovery - Document backfill command in README: airflow dags backfill -s START -e END ecommerce_market_etl |
| TEST | Chaos Engineering Tests - Test 1 — Kill DB during load: docker pause postgres mid-run → verify rollback + FAILED status + alert - Test 2 — Corrupt staging file: delete staging JSON before transform task → verify validate fails cleanly - Test 3 — Duplicate DAG run: trigger same execution_date twice → verify idempotency holds - Test 4 — Empty API response: mock empty JSON → verify pipeline completes with 0 rows, no crash |

| Day 24 Wed | Tasks & Deliverables |
| --- | --- |
| REVIEW | Sprint 3 Review & Airflow DAG Audit - Review DAG in Airflow UI: all tasks green on a clean run - Check Airflow logs for any WARNING or ERROR noise to clean up - Verify all secrets are in Airflow Variables/Connections — none in dags/ source files - Tag release v0.3.0-sprint3 and push to Git |

SPRINT 3 — DEFINITION OF DONE

| # | Definition of Done — Acceptance Criterion | Status |
| --- | --- | --- |
| 1 | DAG ecommerce_market_etl is visible in Airflow UI and runs successfully end-to-end (all 5 tasks green) | ☐ Pending |
| 2 | Scheduled trigger fires at 00:00 daily — confirmed via Airflow 'Next Run' display | ☐ Pending |
| 3 | Network failure (timeout) causes retry with backoff — verified in Airflow task log | ☐ Pending |
| 4 | Slack/email notification received on both SUCCESS and FAILURE scenarios | ☐ Pending |
| 5 | Backfill for 7 past days creates 7 pipeline_run rows with correct execution_dates | ☐ Pending |
| 6 | max_active_runs=1 prevents concurrent DAG runs — verified by triggering manually twice | ☐ Pending |
| 7 | All 8 error scenarios from SRS Section 3.5 tested and handled correctly | ☐ Pending |
| 8 | No hardcoded credentials in any DAG or ETL file (grep -r 'password\¦secret' dags/ etl/ = 0 results) | ☐ Pending |

| # SPRINT 4 — VISUALIZATION & HARDENING Phase 6 + Phase 7 ¦ Timeline: Day 22–30 | Week 4 of 4 sprints |
| --- | --- |

SPRINT GOAL

By end of Sprint 4, the developer can: - Open Metabase and see 4+ interactive charts with real data from PostgreSQL - Share the dashboard URL with a non-technical stakeholder and they can use the filters - Run docker compose up on a fresh machine and have the full system working in < 5 min - Demonstrate the project with a clear README, architecture diagram, and recorded walkthrough

PHASE 6 — Visualization & Dashboard (Day 22–27)

| Day 22–23 Mon–Tue | Tasks & Deliverables |
| --- | --- |
| CONFIG | Metabase Setup & Database Connection - Access Metabase at localhost:3000 — complete initial setup wizard - Add PostgreSQL connection: host=postgres, port=5432, db=ecommerce_db, user/pass from .env - Verify Metabase can query products_market with a native SQL question - Create a Metabase Collection: 'E-Commerce Market Analysis' - Run at least 5 days of data ingestion (or backfill) before building charts — need historical data |

| Day 24–25 Wed–Thu | Tasks & Deliverables |
| --- | --- |
| CODE | Core Dashboard Charts (Required — FR-V01 to FR-V05) - Chart 1 (Bar): Average price by category — GROUP BY category, AVG(price). Add filter: date range - Chart 2 (Table): Top 10 products by rating — ORDER BY rating DESC, show: name, category, price, rating, review_count - Chart 3 (Line): Daily product count trend — GROUP BY extraction_date, COUNT(*). Shows data freshness - Chart 4 (Table/Bar): Pipeline run history — from pipeline_runs table, show status per day (green/red) - Chart 5 (Scorecard): Today's data quality score from latest pipeline_runs row - Add global filters to dashboard: date_range, category. Set auto-refresh to 24h |
| CODE | Bonus Charts (Differentiation) - Chart 6 (Bar): Price distribution histogram — bucket prices into ranges (0–10, 10–50, 50–100, 100+) - Chart 7 (Scatter): Rating vs review_count — spot highly-reviewed vs highly-rated products - Chart 8 (Table): Rejected records log — last 7 days of rejected_records with reason breakdown |

| Day 26–27 Fri–Sat | Tasks & Deliverables |
| --- | --- |
| CODE | Analysis SQL Queries Library - Write sql/queries/avg_price_by_category.sql — parameterized by date range - Write sql/queries/top_rated_products.sql — parameterized by category and limit - Write sql/queries/daily_pipeline_health.sql — join pipeline_runs with products_market counts - Write sql/queries/price_trend_over_time.sql — rolling 7-day average price per category - Add all queries to README with example usage and expected output |

PHASE 7 — Hardening, Testing & Documentation (Day 26–30)

| Day 26–27 Fri–Sat | Tasks & Deliverables |
| --- | --- |
| TEST | Final Full System Test Suite - Run full pytest suite: pytest tests/ -v --cov=etl --cov-report=html — screenshot coverage report - Verify coverage >= 80% on all etl/ modules - Perform 'fresh machine test': git clone, copy .env.example to .env, docker compose up — time it - Verify complete setup < 5 minutes (excluding docker image pull time) - Manually trigger DAG 3 times — verify idempotency across all 3 runs |

| Day 28 Sun | Tasks & Deliverables |
| --- | --- |
| DOCS | README & Architecture Documentation - Complete README.md with: Project Overview, Architecture Diagram (ASCII or Mermaid), Prerequisites - Add sections: Quick Start (docker compose commands), Configuration (.env variables explained) - Add section: Running the Pipeline (manual trigger + scheduled), Backfill Instructions - Add section: Dashboard Access, Testing (pytest commands), Troubleshooting FAQ - Write ARCHITECTURE.md with data flow description and component responsibilities - Add Mermaid diagram of DAG task flow and data pipeline to README |

| Day 29 Mon | Tasks & Deliverables |
| --- | --- |
| REVIEW | Code Quality Final Pass - Run flake8 . --max-line-length=120 — fix all issues - Run black . for consistent formatting - Ensure all modules have module-level docstrings - Remove all TODO comments or convert them to GitHub Issues - Review all print() statements — replace with proper logging (loguru or stdlib logging) - Tag final release v1.0.0 with descriptive release notes on GitHub |
| DOCS | Presentation Preparation - Prepare 5-minute demo script: run DAG → show logs → open Metabase → show dashboard - Screenshot or screen-record: Airflow DAG Graph View, successful run log, Metabase dashboard - Prepare answers to likely review questions: 'How do you handle duplicates?', 'What if the API is down?' - Add screenshots folder to repository with key UI screenshots for README |

| Day 30 Tue | Tasks & Deliverables |
| --- | --- |
| REVIEW | Final Review & Project Submission - Complete final acceptance criteria checklist (see below) — all items must be ✅ - Verify Metabase dashboard is accessible and showing data from last 7 days - Verify docker compose up works on a freshly pulled repository - Push final commit with tag v1.0.0 and create GitHub Release with release notes - Submit project with: GitHub URL, Metabase dashboard screenshot, Airflow DAG screenshot |

SPRINT 4 — DEFINITION OF DONE

| # | Definition of Done — Acceptance Criterion | Status |
| --- | --- | --- |
| 1 | Metabase dashboard shows all 5 required charts (FR-V01 to FR-V05) with real data | ☐ Pending |
| 2 | Dashboard date range and category filters work correctly | ☐ Pending |
| 3 | README.md is complete with Quick Start, architecture diagram, and demo instructions | ☐ Pending |
| 4 | Full pytest suite: 0 failures, >= 80% coverage (evidence: coverage HTML report committed) | ☐ Pending |
| 5 | flake8 . returns 0 warnings across all source files | ☐ Pending |
| 6 | Fresh docker compose up completes system setup in under 5 minutes | ☐ Pending |
| 7 | Project demo (5 min): DAG run → logs → Metabase dashboard flow works without errors | ☐ Pending |
| 8 | GitHub repository tagged v1.0.0 with complete release notes | ☐ Pending |

# PROJECT COMPLETION CHECKLIST

| # | Final Acceptance Criterion | Sprint | Status |
| --- | --- | --- | --- |
| 1 | Docker Compose brings full stack online without errors | Sprint 1 | Not started |
| 2 | Extractor fetches real data with retry on network failure | Sprint 1 | Not started |
| 3 | Clean DataFrame produced from raw JSON — no invalid rows remain | Sprint 2 | Not started |
| 4 | Re-running load produces 0 new duplicate rows (idempotency) | Sprint 2 | Not started |
| 5 | Rejected rows logged in rejected_records with reason code | Sprint 2 | Not started |
| 6 | Airflow DAG runs automatically daily at 00:00 | Sprint 3 | Not started |
| 7 | All 8 error scenarios handled (network, DB, schema, dupe, etc.) | Sprint 3 | Not started |
| 8 | Slack/email notification received on SUCCESS and FAILURE | Sprint 3 | Not started |
| 9 | Backfill re-processes 7 past days correctly | Sprint 3 | Not started |
| 10 | Metabase dashboard shows 4+ charts with filters | Sprint 4 | Not started |
| 11 | pytest: 0 failures, >= 80% coverage | Sprint 4 | Not started |
| 12 | No credentials in source code (grep check) | Sprint 4 | Not started |
| 13 | Fresh docker compose up works in < 5 minutes | Sprint 4 | Not started |

⭐ BONUS POINT OPPORTUNITIES (Complete any 3+ for top marks) - PySpark branch: replicate transformer.py logic in PySpark, compare performance - Data quality score metric (% rows passing validation) stored in pipeline_runs - Schema drift detection: pandera alerts on unexpected column changes - CI/CD pipeline: GitHub Actions running pytest on every push - Google Looker Studio: alternative dashboard connected to PostgreSQL via connector - Prometheus + Grafana: pipeline metrics scraping (rows/sec, error rate)